## Sheet1
Week | Project Flask ML | Estimate Normal (hours) | Estimate Worst (hours) | Estimate Best (hours) | Detailed Description
2020-09-28 | Project Planning | 4 | 6 | 3 | weekly plan trello tasks
2020-10-05 | Set up project DevOps | 4 | 8 | 2 | repository GitHub integrate CI integrate CD
2020-10-12 | Deploy Flask ML | 2 | 4 | 1 | create app service deploy initial version
2020-10-19 | Set up monitoring tools | 2 | 4 | 1 | setup health checks
2020-10-26 | "New features added" | TBD | TBD | TBD | "developers add XYZ features"
2020-11-02 | "Application ready to QA" | TBD | TBD | TBD | "QA verification"
2020-11-09 | "Production version" | TBD | TBD | TBD | "clean applicaction for production"
2020-11-16 | "Start maintanace phase" | TBD | TBD | TBD | "monitor application" "support phase"
Goals
Python-based machine learning application in production
Complete CICD from code to delivery
Code always tested and working condition
Formulas:
Week = [Week, row below]-7
Week = [Week, row above]+7